# Objective

Provide step-by-step instructions for executing the Design & Development procedure (P-830-01), completing each supporting form (F-830-001, F-830-002, F-830-003), and ensuring every requirement is met and traceable.

# Applicability

Applies to all personnel responsible for design planning, reviews, outputs, verification & validation, and change management under the QMS.

# Responsibilities and Authorities

- Engineering Lead – Owns the plan, gathers inputs, coordinates reviews, updates forms.

- Program Management – Validates objectives, schedule, resources, and interfaces.

- Quality Representative – Checks compliance content, risk items, and V&V evidence.

- Configuration Management – Controls baselines and form versions.

- Change Control Coordinator – Manages and tracks design change records and plan updates.

# Definitions and Acronyms

| Term | Definition |
| --- | --- |
| D&D Plan (F-830-001) | The controlled workbook capturing all design planning elements. |
| Review Checklist (F-830-002) | The template used at each formal review to verify design requirements. |
| Change Record (F-830-003) | The form used to propose, review, and approve changes to released design outputs. |

# Procedure

## Prepare the D&D Plan (F-830-001)

- Open & Verify

  - Download F-830-001 from the DMS. Confirm document revision in the header matches the QMS baseline.

  - Save a local copy named D&D Plan – [Project] – Rev –.

- Project Identification (Tab: Project)

  - Project / Programme: Enter the exact title from the customer contract.

  - Customer: Enter official legal name.

  - Internal Ref No.: Use the QMS-assigned project code.

  - Plan Owner: Select your name from the Owners dropdown (ensures email notifications).

  - Date Issued: Enter today’s date (YYYY-MM-DD).

  - Review: These fields are locked after approval; any correction requires a Change Record.

- Objectives & Deliverables (Tab: Objectives & Deliverables)

  - Objective: For each row, enter a S.M.A.R.T. goal (e.g., “Validate wing-tip load capacity to 5G”).

  - Deliverable: List concrete outputs (e.g., “Structural analysis report,” “Release 1.0 CAD package”).

  - Review: Ensure at least one objective per project requirement; link to Quality Objectives if applicable.

- Stage-Gate Schedule (Tab: Stage-Gate Schedule)

  - Gate: Select from dropdown (Concept, PDR, CDR, Verification, Validation, Release).

  - Target Date: Enter planned date for gate completion.

  - Entry Criteria: Copy from P-830-01 “Procedure” section for that gate.

  - Exit Criteria: Copy from P-830-01.

  - Gate Sign-off: Leave blank until the actual review—reviewers will enter Name / Date.

  - Review: Verify all gates appear in correct sequence with no blanks.

- Responsibilities & Resources (Tab: Responsibilities & Resources)

  - Role: Enter Process Owner title (e.g., “Lead Stress Engineer”).

  - Person: Pick from dropdown of authorized personnel.

  - Competence: Note certification or qualification (e.g., “FAA DER”).

  - Special Tools / Labs: List any equipment or facility requirements.

  - Budget: Enter approved budget code or amount.

  - Review: Ensure every deliverable and V&V task has an assigned resource.

- Applicable Requirements (Tab: Applicable Requirements)

  - Requirement: Paste full title (e.g., “Customer Spec ABC-123 Rev C”).

  - Source: Select “Contract,” “Regulation,” “Standard,” or “Policy.”

  - Revision: Enter the exact issue date or code.

  - Status: Use dropdown to mark Complete, Clarification Needed, or Conflict.

  - Notes / Link: If Conflict, attach a Customer Waiver or DCR link here.

  - Review: No row left blank; all conflicts must have a linked waiver or resolution.

- Risk & Opportunity Summary (Tab: Risk & Opportunity)

  - ID: Enter R-001, R-002, …

  - Type: Select Risk or Opportunity.

  - Description: One-line summary (e.g., “Potential fatigue crack at joint A”).

  - Initial Severity & Likelihood: Use dropdown (H/M/L or 1–5).

  - RPN: Verify automatic calculation or enter S×L as per R-Matrix.

  - Action: Brief mitigation or exploit plan.

  - Owner: Select responsible function/person.

  - Target Completion: Date.

  - Residual Scores: Complete when action is done.

  - Status / Close Date: Mark Closed when verified; enter date.

  - Evidence: Hyperlink to risk-analysis report in DMS.

  - Review: All high risks (RPN>Threshold) must have mitigation actions and owners.

- V&V Strategy (Tab: V&V Strategy)

  - Ref.: Assign V1, V2, …

  - Method: Describe test or analysis (e.g., “Thermal cycling per ASTM E123”).

  - Function: Select Engineering, Quality, or external lab.

  - Acceptance Criteria: Copy from output requirement.

  - Planned Date: When test/analysis will occur.

  - Evidence Link: After execution, paste DMS link to report.

  - Review: Ensure each high-risk item and special characteristic has at least one V&V entry.

- Information Interfaces (Tab: Interfaces)

  - Interface ID: I-001, I-002, …

  - From / To: Select functions from dropdown.

  - Info Type: Describe artifact (e.g., “CAD model Rev B”).

  - Trigger: E.g., “PDR exit,” “Monthly update.”

  - Media: Select “DMS,” “PLM,” “Secure e-mail.”

  - Owner: Person responsible for transfer.

  - Ack Req: Y/N.

  - Link: Hyperlink to the file or template.

  - Review: Confirm each downstream function has at least one input interface.

- Gate Records (Tab: Gate Records)

  - Gate: Dropdown as above.

  - Record: List document title (e.g., “Design Review Minutes”).

  - Revision: Current revision code.

  - Approver: Name or function.

  - Approval Req: Y/N.

  - Storage Link: DMS folder or file hyperlink.

  - Review: No gate marked “Proceed” without all Approval Req=Y items signed off.

- Change-Control Rules (Tab: Change Rules)

  - Type: Dropdown “Contract Change,” “Design Change,” “Config Update.”

  - Initiator: Function or name.

  - Reviewers: List required participants.

  - Authority: Who signs the change.

  - Impact Assmt: Y/N.

  - Notif Req: Y/N.

  - Notif Method: E-mail, letter, portal.

  - Artifact: F-830-003 or F-812-002 form name.

  - Review: Ensure every change type in your project has an associated rule row.

## Conducting Design Reviews (F-830-002)

- Launch the Review Checklist

  - Open F-830-002 Design Review Checklist.xlsx from the DMS.

  - Rename the sheet tab to Checklist – [Project] – [Gate] – [YYYY-MM-DD].

  - Update the file name to include project code and gate, e.g. ProjectX_CDR_2025-05-20.xlsx.

- Populate Review Metadata

  - In the header area, enter:

    - Project / Programme (exact contract title)

    - Customer (legal entity)

    - Review Date (YYYY-MM-DD)

    - Review Type (select from dropdown: Concept, PDR, CDR, Verification, Validation)

    - Chairperson (name running the meeting)

    - Minute-Taker (name recording minutes)

    - Participants (comma-separated list of attendees)

- Load Checklist Items

  - Copy the 26 items (A-1 through H-2) from the Design & Development procedure (P-830-01) into the Checklist Item column, one per row.

  - Confirm each ID (e.g., A-1, B-2) aligns with the procedure’s wording.

- Record Findings

  - For each checklist row:

    - Status: choose OK, Issue, or N/A.

    - Evidence / Comments: paste a hyperlink to the specific document/page (e.g., DMS://ProjectX/Drawings/DRW-123.revB) or type a brief note.

  - If Status = Issue:

    - Enter an Owner (from the Owners dropdown).

    - Enter a Target Date when the issue must be resolved (YYYY-MM-DD).

- Review and Escalate Issues

  - Apply the filter on Status to show only Issue rows.

  - Confirm each issue has an Owner and Target Date; unresolved items cannot be skipped.

  - Export this filtered list (optional) for offline tracking.

- Capture Gate Outcomes

  - In the sign-off block: Chairperson and Quality Representative sign or e-sign and date.

  - In the D&D Plan’s Gate Records tab:

    - Add a row for this gate if not already present.

    - Copy each document checked, its revision, and link back to the saved checklist file.

    - Mark Approval Required = Yes and list the approver names.

- Save and Archive

  - Save the completed checklist back into the project’s folder in the DMS under …/Design Reviews/.

  - Lock the file (read-only) and set permissions so only Quality and Configuration Management can modify it.

## Managing Design Changes (F-830-003)

- Open the Change Record

  - Retrieve F-830-003 Design Change Record.docx from the DMS.

  - Save a working copy named DCR_[Project]_[YYYY-MM-DD]_[ShortTitle].docx.

- Complete Change Fields

  - Change ID: use the project’s change sequence (e.g., X-DCR-007).

  - Date Requested: today’s date.

  - Originator / Department: your name and function.

  - Change Title / Description: concise title and full description.

  - Reason for Change: reference issue, customer request, or risk trigger.

  - Affected CIs: list all drawings, software modules, BOMs impacted.

  - Impact Summaries: fill out Performance/Safety and Cost/Schedule sections.

  - Risk Assessment Summary: cite R-ID from the Risk worksheet and residual risk.

  - Notification Required: select Yes/No; if Yes, enter Notification Date.

  - Implementation Plan & Schedule: bullet key steps and dates.

  - V&V Required: select Yes/No; if Yes, link to V&V Strategy entry.

  - Approval Signatures: leave blank for stakeholders to sign digitally or on paper.

- Attach Supporting Documents

  - Insert hyperlinks or embed: impact-analysis spreadsheets, updated drawings, risk-register excerpts, test plans.

- Route for Review

  - Via the DMS workflow, send the DCR to the Reviewers group: Engineering Lead, Quality, Configuration Management, Program Management.

  - Set a 2-business-day review deadline in the workflow.

- Obtain Approvals

  - Each Reviewer provides electronic signature and comments.

  - Quality confirms compliance implications; Program Management confirms resource impact; Configuration Management confirms baseline readiness.

- Finalize Change

  - Enter the final Notification Date if customers or regulators must be informed.

  - Update the Implementation Complete date and signature once the change is in production or service.

- Update the D&D Plan

  - Open F-830-001, go to each affected tab (Inputs, Stage-Gate Schedule, V&V Strategy, Risk Register).

  - Insert or update rows with new values; highlight changed cells in yellow for the first revision.

  - Increment the plan’s Rev in the header (e.g., – → A).

  - In Revision History, add a new row with Rev A, date, sections changed, summary (“Added DCR-007 inputs & updated V&V schedule”), and your initials.

- Publish and Notify

  - Save the revised plan to the DMS under …/Design Plans/ naming it D&D Plan_[Project]_Rev A.xlsx.

  - Distribute an email notification to all stakeholders with a link to the new plan and DCR.

## Implementation of the Procedure

- Publication

  - Configuration Management publishes P-830-01, WI-830-001, and all forms in the QMS document library.

  - Add links to the QMS Intranet homepage under “Design & Development.”

- Training

  - Schedule a 2-hour workshop for Engineering, Program Management, and Quality teams:

    - Walk through each tab of F-830-001 live in Excel.

    - Conduct a mock PDR using F-830-002.

    - Demo a sample DCR submission.

  - Record attendance and store training records in the Training LMS.

- Access Control

  - DMS permissions:

    - Read-only for all users.

    - Edit rights for Engineering Lead and Configuration Management on the Plan.

    - Form rights for any originator on F-830-002 / F-830-003.

- Monitoring & KPI

  - Quality collects the following monthly:

    - Number of open review issues past target date.

    - Average turn-around time for DCR approvals.

  - Report KPIs at Management Review; assign corrective actions for any lagging metrics.

- Audit & Continuous Improvement

  - Internal Audit annually: sample one project’s full D&D Plan, Review Checklist, and DCRs.

  - Generate a non-conformance report for gaps, update the procedure/work instruction, and retrain affected staff.

- Document Control

  - Any change to P-830-01 or WI-830-001 itself follows the Control of Documented Information procedure:

    - Submit a Document Change Request.

    - Peer-review in a Document Review Board.

    - Release with a new revision and update the Document Master List.

References

- Design & Development procedure (P-830-01)

- Control of Documented Information procedure (QP-750-01)

- Corrective Action procedure (P-1020-01)

Documented Information

- Completed Design & Development Plan (F-830-001)

- Completed Design Review Checklist(s) (F-830-002)

- Approved Design Change Records (F-830-003)

Revision History

| Rev | Date | Section | Change Summary | Authorized by |
| --- | --- | --- | --- | --- |
| – | – | All | Expanded to detailed, worksheet-by-worksheet instructions | OQC |