# Purpose

- This procedure defines the Risk Management process and application for identifying risks for Jobs whose risks are beyond the normal scope of business for The Organization.

Responsibilities

- The VP of Operations is responsible for the risk management process for the projects and for accepting or rejecting the level of risk for the project.

- Managers and Supervisors are responsible for providing input to the process for identifying risks as applicable.

Definitions

| Term | Definition |
| --- | --- |
| Risk | a measure of the inability to achieve overall program objectives within defined cost, schedule and technical constraints. |
| Risk Management | the processes concerned with identifying, analyzing and responding to project risk. |
| Risk Identification | determining which risks are likely to affect the project and documenting the characteristics of each. |
| Risk Analysis | the process of evaluating risk and risk interactions to assess the range of possible project outcomes. |
| Risk Mitigation | reducing the likelihood or consequence to acceptable levels. |

Equipment or Software

- None

Process

- Document the risk identification approach and attach to Contract Review if risks could be moderate or severe. Risks can be identified using:

  - Program/Job Requirements

  - Customer Concerns and Issues

  - Cost and Schedule

  - Test, Logistics and Support Date

  - Vendor Assessments

  - Failure Mode and Effects Analyses

- Document any additional risks in a Risk List. Include:

  - The risk description/name

  - A risk statement that includes the root cause, possible outcomes, impact and consequence of the risk.

  - If required assign risk owner responsible for mitigation plan

- Assess and Prioritize the risks

  - Rank the identified risk items according to degree of risk (high, moderate, low) or quantitatively in accordance with program needs

- Develop and Implement Risk Handling Approaches

  - Risk Mitigation Plans shall be implemented when the risk is deemed high and some aspect of the risk is controllable by the program.

  - Risk owners document a Risk Mitigation plan, including as applicable:

    - Task IDs, Task names

    - Start and finish dates

    - Cost of task

    - Criteria for success of the risk mitigation plan

  - For high risks that have no cost-effective mitigation possibilities, the risk owner documents a contingency plan. Include:

    - Contingency preparation tasks

    - Contingency tasks

    - Decision criteria for implementing the contingency tasks

  - The mitigation and contingency plans are submitted to the VP of Operations for approval.

- Track and Report

  - Reassessments and risk closures are done in accordance with the Risk Management Plan. Tracking may include:

    - Identifying new risks

    - Reassessing each risk on a periodic basis

    - Closing risks

    - Adjusting mitigation plans or developing new mitigation plans

    - Adjusting schedules and budgets.

  - The VP of Operations is responsible for approving all changes.

| 0 - 9 = Low Risk |  | Severity |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 10 – 19 = Moderate Risk |  | Insignificant - 1 | Minor - 2 | Moderate - 3 | Major - 4 | Catastrophic - 5 |
| 20 - 25 = Severe (unacceptable) |  |  |  |  |  |  |
| High risks should be mitigated, if possible, to reduce risk. |  |  |  |  |  |  |
| Likelihood of Occurrence | Almost Certain 5 | 5 | 10 | 15 | 20 | 25 |
|  | Will Probably Occur 4 | 4 | 8 | 12 | 16 | 20 |
|  | Possible Occurrence 3 | 3 | 6 | 9 | 12 | 15 |
|  | Remote Possibility 2 | 2 | 4 | 6 | 8 | 10 |
|  | Extremely Unlikely 1 | 1 | 2 | 3 | 4 | 5 |

Control of Revision Table

| Revision | Changes | Created by | Approved by | Date of approval |
| --- | --- | --- | --- | --- |
| Draft | New document | Brian Olea (OAQC) |  |  |