## INSTRUCTIONS
Using the Operational Risk Register
Purpose:
This workbook tracks operational and compliance risks for the organization in line with AS9100D Clause 8.1.1.
Tabs:
• SCORING TABLE – Definitions for scoring and the risk matrix.
• RISK REGISTER – Continuous log. Fill one line per risk.
• DASHBOARD – Automatic roll‑up of open risks by category.
Steps:
1. Go to RISK REGISTER and enter a new row when a risk is identified.
2. Select Severity, Likelihood, Detection (1–10). The RPN and category calculate automatically.
3. Add mitigation, owner and target date. Update Status and residual scores when actions close.
4. Review the Dashboard before Management Review.
Scoring quick view:
Severity: 1 (no effect) … 10 (catastrophic safety / regulatory impact)
Likelihood: 1 (remote, >5 yr) … 10 (weekly / inevitable)
Detection: 1 (certain) … 10 (undetectable)
Risk Category thresholds:
RPN < 100 → Low (green)
100–199 → Medium (yellow)
200–299 → High (orange)
≥ 300 → Critical (red)
Maintain this file as a living document. Protect formulas; add rows as needed.

## SCORING TABLE
Severity / Likelihood / Detection – 1‑10 Definitions
Score | Definition (apply to S, L or D)
1 | No impact / Remote / Always detected
3 | Minor internal issue / Unlikely / High detection
5 | Moderate customer effect / Possible / Moderate detection
7 | Significant rework or reg. concern / Likely / Low detection
10 | Catastrophic safety or recall / Frequent / Undetectable
Risk Matrix (Likelihood × Severity)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
10 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100
9 | 9 | 18 | 27 | 36 | 45 | 54 | 63 | 72 | 81 | 90
8 | 8 | 16 | 24 | 32 | 40 | 48 | 56 | 64 | 72 | 80
7 | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 56 | 63 | 70
6 | 6 | 12 | 18 | 24 | 30 | 36 | 42 | 48 | 54 | 60
5 | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50
4 | 4 | 8 | 12 | 16 | 20 | 24 | 28 | 32 | 36 | 40
3 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30
2 | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10

## RISK REGISTER
Risk ID | Date Identified | Topic / Area | Risk Description | Potential Impact | Assessment Frequency | Quantified? (Yes/No) | Metrics | Monitored Over Time? (Yes/No) | Severity | Likelihood | Detection | RPN | Risk Category | Mitigation Plan | Owner | Target Date | Status | Residual Severity | Residual Likelihood | Residual Detection | Residual RPN | Residual Category | Comments
RISK-001 | 2025-05-05 | Supply Chain | Global alloy shortage could delay deliveries | Schedule impact | Weekly | YES | Supplier OTD % | YES | 7 | 6 | 4 | Dual sourcing, expedite options | Supply Chain | 2025-06-30 | Open
RISK-002 | 2025-05-05 | FOD | Foreign Object risk in assembly | Potential flight safety | Daily | YES | FOD count | YES | 9 | 3 | 5 | Tool control, FOD sweeps | Quality | 2025-05-31 | Open
RISK-003 | 2025-05-05 | Counterfeit Parts | Unapproved parts risk | Nonconforming product | Per PO | NO |  | YES | 8 | 2 | 6 | Approved vendor list only | Procurement | 2025-07-15 | Open
RISK-004 | 2025-05-05 | Calibration | Expired torque wrench calibration | Quality escape | Monthly | YES | Past due tools | YES | 6 | 4 | 3 | Auto calibration alerts | Metrology | 2025-05-25 | Open
RISK-005 | 2025-05-05 | Cybersecurity | Network intrusion risk | Data loss | Continuous | YES | Incidents | YES | 7 | 3 | 5 | Firewall, MFA | IT | 2025-08-01 | Open

## DASHBOARD
Risk Summary (counts by category)
Category | Open Items
Critical | 0
High | 0
Medium | 0
Low | 0